Recommended Workshop Attendees:

Leaders of each Team; Entire Steering Team; 1-3 employee representative from each team

Preparation:

All teams, including the Steering Team, will complete the All Teams Joint Planning Worksheet (aka “Look Back and Look Forward Activities”) prior to the All Teams Joint Planning Workshop.

In some organizations, the draft plans created by the teams via the Planning Worksheet are submitted in writing to the Steering Team prior to the All Teams Joint Planning Workshop for distribution to all attendees at the Workshop; in other organizations, they provide a verbal report only (per the Worksheet instructions) at the Joint Planning Workshop.

Steering Team to communicate to teams if written draft plan are to be submitted prior to the Workshop, and the due date.

As well as coordinating with the teams for the Workshop preparation, the Steering Team will tend to all logistics for the event, such as securing the room, food/beverages, and any workshop supplies (flip chart paper, markers, etc.).

A member of the serving team will serve as a facilitator during the workshop.

Agenda:  Order of activities with estimated timing based on allotting 3-4 hours for the workshop

10 minutes:  Welcome, Introductions, Positivity/Ice-Breaker Activity

20-30 minutes:  Look Back Reports (each team – 3-5 minutes – see the format for team presenters from All Teams Joint Planning Worksheet). Capture the Wins/Success/Progress on a Whiteboard or Flip Chart Paper (Note: some organizations create a celebration banner to write these on so they can be posted in the organization). Capture the Barriers/Struggles on a Whiteboard or Flip Chart Paper.

30 minutes: Facilitated Group Discussion – Barriers/Struggles (select 2-3 common barriers that were reported from the teams during the Look Back reports; break attendees into 2-3 diverse groups and assign one of the common barriers. Each group to follow the process below for their group’s assigned barrier/struggle (steps 1-3 for 20 minutes; step 4 for 10 minutes):

- If this barrier/struggle was eliminated, what would it look/feel like? (e.g., if on a 1-10 scale, we were a 10 at this, what actions/behaviors would we see, what results/outcomes would we see).

- Describe in more detail, the current barrier/struggle. What does it look/feel like, what actions behaviors do we see, what impact is it having on our progress/results/outcomes? If you had to give this barrier/struggle a rating on a 1-10 scale (1 being the worst it could be, and 10 being the response you gave to #1 above).

- Brainstorm all the actions that could be taken to eliminate this barrier/struggle to get closer to a rating of 10? Pick your top three actions that you recommend be taken.

- Each team to give a 3-5 minute report of their answers to questions 1, 2 & 3 to all attendees at the workshop. All answers to question #3 should be provided to the Steering Team for further consideration and actions to remove barriers.

15 Minute BREAK

10 minutes – Look Forward – CEO – Vision for Year Ahead (recap of mission, vision, key strategies, organizational goals)

30-70 minutes (depending on # of Teams and length of their reports):  Look Forward Reports (each team – 5-10 minutes – see the format for team presenters from the Worksheet);

At the end of each team’s report, discuss:

- Do the team’s proposed action plans keep them aligned with their team’s purpose?

- Is the team’s plan “too easy?” Or, “too aggressive?” Or, “Just right?” (e.g., on the higher end of difficulty, but not impossible, related to the quantity and complexity of work).

- Is there a combination of new actions as well as circling back (study/adjust) to prior initiatives?

10 minutes – Look Forward Discussion. After all teams have provided their Look Forward reports, discuss:

- Is there duplication of efforts identified in 2 or more teams? Or opportunities for teams to collaborate?

- Is there a major priority that is going unaddressed by the team(s)?

- If all teams are successful with their action plans, will there be major contributions to the organization’s goals and priority strategies?

10 minutes – Team Huddles – Is there anything a team may need to do, in follow up to the earlier discussions, to adjust/finalize their action plans?

5-15 minutes - Wrap Up, Evaluation, Call-to-Action (individual teams’ action plans finalized in writing, by a specified date, and provided to the Steering Team).