Phase I Timeline:

| √ | Start-Up Activities | Notes/Comments |
| --- | --- | --- |
|  | Executed HIPAA/Business Associate Agreement |  |
|  | Confirm Initiative Champion(s) |  |
|  | Establish Weekly Phase I Calls |  |
|  | Schedule date(s) / initiate logistics for On-Site Visit 1 |  |
|  | Schedule date for On-Site Visit 2 |  |
|  | Develop and implement communication for organization-wide announcements & updates regarding this phase of the initiative | prn |
|  | Submit requested data & information to Capstone |  |
|  | Baseline Surveys (Change Challenges, Solutions Checklist, Leadership Learning Needs Assessment) – Survey Links/Instructions provided |  |
|  | Define the Initiative Team Structure for the System and Affiliates |  |
|  | Schedule & hold Steering Team Meetings as needed to accomplish Phase I objectives | prn |
|  | Select team leaders |  |
|  | Steering Team to complete Vision/Why activity | After Steering Team assembled - by ______ |
|  | Select/Affirm a “branded” name for the Journey/Initiative | After Steering Team assembled - by ________ |
|  | Select team members | After Steering Team assembled - by ________ |
|  | Provide Capstone with contact information (name/title/email/phone) for all Steering Team members/Team leaders for invitations to group coaching calls | After Steering Team assembled - by ________ |
|  | Team plans and annual leadership development plan developed by Capstone and provided to partner | 2-3 weeks prior to Visit 1: ________________ |
|  | Establish timeline for goal cycle periods (Designate Goal Cycle internal champions if timeline requires) | Determine before Action Plans finalized on ________ |
|  | Each team to hold a minimum of 1 meeting before On-site Visit 1 (team orientation video, commitment statements, plan review, getting to know you activity) | After team action plans received and before Visit 1 |
|  | Establish Phase II Steering Team meeting schedule | Initiate after Visit 1 |
|  | Establish Monthly Phase II Check-In Calls (x6 months) | Initiate after Visit 1 |